## Defects
ID | Work Item Type | Title | State | Assigned To | Tags | Severity | Issue Links
8758 | Bug | While creating a Move-In Request, when user selects the "People of Determination" option as Yes and enter details, the system does not save this. After request is created, it shows the value as "N/A" instead of "Yes" and the provided details are missing. | New | devesh.kumar@techcarrot.ae | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8758
8847 | Bug | Backoffice: Pagination still appears even when filtered requests fit on a single page. | New | Krishnan Kannan | Move in | 4 - Low | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8847
8902 | Bug | Backoffice: MoveIn: Message displays twice while creating HHC Move In request successfully | New | Krishnan Kannan | Move in | 4 - Low | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8902
8903 | Bug | Mobile App: Profile Section is not accessible in Mobile App. It is showing error message " Something went wrong" and then loading image is showing which does not disappear. | New | Sivabalan Vijayakumar | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8903
8909 | Bug | Backoffice: Close Request button changes to white on hover. | New | Krishnan Kannan | security | 4 - Low | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8909
8913 | Bug | Back office: Security Admin Credentials: Move In should be available in Screen Group Mapping under "user privilege Management" in Security Admin Dashboard | New | Aminda Weerawardhana | security | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8913
8898 | Bug | Back office: Title of the Validation message on all the request type is not correct | New | Krishnan Kannan | Move in | 4 - Low | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8898
8922 | Bug | BackOffice: Move-In: Alignment issue in HHC Company details while editing a request. | New | Krishnan Kannan | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8922
8927 | Bug | Backoffice: Tenancy Contract Start Date field does not allow selecting past dates | New | Krishnan Kannan | Move in | 4 - Low | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8927
8928 | Bug | Backoffice: Emirates ID Expiry Date field does not allow selecting future dates beyond one month | New | Krishnan Kannan | Move in | 4 - Low | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8928
8929 | Bug | BackOffice: Move-In: Incorrect User Details Displayed After Viewing HHC Request | New | Krishnan Kannan | Move in | 4 - Low | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8929
8924 | Bug | BackOffice: Move-In: Country Code shows “N/A” in HHC Company request View screen | New | devesh.kumar@techcarrot.ae | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8924
8931 | Bug | Backoffice: Incorrect Error message displayed for Unit Permit Start and Expiry date while creating HHC request from Backoffice | New | Krishnan Kannan | Move in | 4 - Low | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8931
8944 | Bug | Backoffice: Field alignment issue in Move-in Request form of HHO Company. | New | Krishnan Kannan | Move in | 4 - Low | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8944
8945 | Bug | Backoffice: Field alignment issue in HHO Owner Move-in Request form | New | Krishnan Kannan | Move in | 4 - Low | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8945
8946 | Bug | Backoffice: Field alignment issue in Tenant Move-in Request form | New | Krishnan Kannan | Move in | 4 - Low | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8946
8947 | Bug | Backoffice: Move-in Type, Created Date Range Start and Created Date Range End filters are not working on Move-in Request Dashboard. | New | devesh.kumar@techcarrot.ae | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8947
8949 | Bug | Backoffice: “If Available” text incorrectly displayed in Emirates ID Number field on HHO Request Creation Form | New | Krishnan Kannan | Move in | 4 - Low | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8949
8950 | Bug | Backoffice: Missing Serial Number in MIP and Welcome Pack List | New | Rahees Khan | Move in | 5 - Suggestion | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8950
8951 | Bug | Back office: Move in: When Owner created request from Mobile app, User type shown as "tenant in Email Notification | New | devesh.kumar@techcarrot.ae | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8951
8952 | Bug | Back office: Move in: Email notification missing information: Start date (lease): and End date (lease) | New | devesh.kumar@techcarrot.ae | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8952
8953 | Bug | Backoffice: Validation errors displayed for non-existent fields in HHO Company Request Creation Form. | New | devesh.kumar@techcarrot.ae | Move in | 2 - High | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8953
8954 | Bug | Backoffice: Asterix need to be removed from upload doc section while editing Move-in Requests (Tenant, HHO Unit, HHO Company) | New | Deepthi Jangareddi | Move in; security | 4 - Low | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8954
8955 | Bug | Backoffice: Email notification for HHO Company Move-in Request shows incorrect user type as "Owner" when move request created from OneApp | New | devesh.kumar@techcarrot.ae | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8955
8956 | Bug | Backoffice: Security Admin: Move in: Admin user can not close any of the approved request | New | devesh.kumar@techcarrot.ae | security | 2 - High | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8956
8957 | Bug | Back office: Move In: Move-In Form fields refresh after navigating back from Notification Bell | New | Krishnan Kannan | Move in | 4 - Low | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8957
8948 | Bug | Backoffice- Emirates ID Number field accepts alphabets and not maintaining the standard format in emirates ID field after tab out in HHC form. | Closed | Mohammad Tabreze Karimee |  | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8948
8932 | Bug | Backoffice: Move in: HHC New request Creation: Unit Permit Start and End date displays Twice | Closed | Mohammad Tabreze Karimee |  | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8932
8933 | Bug | Backoffice: Move in: Tenancy Contract Start Date field should not be available in HHC new Request | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8933
8925 | Bug | BackOffice: Move-In: Trade License Expiry Date disappears while editing the HHC Move-In request | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8925
8926 | Bug | BackOffice: Move-In: Representative Name not displayed in HHC Request View screen | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8926
8923 | Bug | BackOffice: Move-In: While viewing the HHC Company request, Extra field displayed that is not defined in One App, Figma, or BRD | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8923
8899 | Bug | Back office: Clicking on Breadcrumb "Dashboard" under Create Move In Request redirecting to Main dashboard but not Move In Dashboard | Closed | Deepthi Jangareddi | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8899
8901 | Bug | Backoffice: Move In: In HHC New Request Creation, message should be Unit Permit end date instead of Unit Permit Expiry Date | Closed | Mohammad Tabreze Karimee | Move in | 4 - Low | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8901
8914 | Bug | BackOffice: Move-In: Missing fields in HHC Company Form compared to BRD. | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8914
8915 | Bug | Backoffice: Few fields are missing in HHO new request creation Screen | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8915
8916 | Bug | BackOffice: Move-In: Extra field displayed in HHC Company Form compared to BRD. | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8916
8917 | Bug | Backoffice: Master Data Setup: User is able to create new Request even if Welcome pack and MIP are inactive for that user | Closed | Mohammad Tabreze Karimee | Master Data Setup | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8917
8918 | Bug | Back office: Move in Request Email Attachment has text "Status: approved". Here text approved should be in Proper case | Closed | Mohammad Tabreze Karimee | Master Data Setup | 4 - Low | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8918
8919 | Bug | Backoffice: In the Move in Request approved email Request type is undefined | Closed | Mohammad Tabreze Karimee | Master Data Setup | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8919
8920 | Bug | Backoffice: Move in: In Move in Request Update email, there is no MIP attachment, and One Sobha Header is not displayed | Closed | Mohammad Tabreze Karimee | Master Data Setup | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8920
8921 | Bug | Back office: Movein : In Move request approved Email, no Welcome pack attachment is available | Closed | Mohammad Tabreze Karimee | Master Data Setup | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8921
8910 | Bug | Backoffice: Move In: Tenancy new Request: When user create New Tenant Request, application display successful message, but it does not move back to Move in Dashboard instead it remains stay on Create Tenant Request screen | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8910
8911 | Bug | Back office: If Tenancy contracts start date is greater than Move In date, application displays validation error message which is not user friendly | Closed | Mohammad Tabreze Karimee | Move in | 4 - Low | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8911
8912 | Bug | BackOffice: Move-In: Super Admin details displayed in Cancelled View screen for all user types | Closed | Mohammad Tabreze Karimee | security | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8912
8904 | Bug | Backoffice: Past dates allowed for Actual Move-in Date field when closing a request by Security. | Closed | Mohammad Tabreze Karimee | security | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8904
8905 | Bug | BackOffice: When the user closes the Move-In request, the system takes around 5–6 seconds to redirect to the previous screen. | Closed | Mohammad Tabreze Karimee | security | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8905
8906 | Bug | Backoffice: Move-out button missing on closed requests. | Closed | Mohammad Tabreze Karimee | security | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8906
8907 | Bug | Backoffice: Account Renewal button missing on closed requests | Closed | Mohammad Tabreze Karimee | security | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8907
8908 | Bug | BackOffice: Move-In: Super Admin details are displayed in the User Details section of the Close Request View screen | Closed | Mohammad Tabreze Karimee | security | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8908
8848 | Bug | Backoffice: Move-In: Emirates ID number field drop-down missing in Tenant request creation form | Closed | Deepthi Jangareddi | Move in | 4 - Low | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8848
8850 | Bug | Backoffice: Uploaded image is cut from the top. | Closed | Mohammad Tabreze Karimee |  | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8850
8851 | Bug | One APP: Status update from Back Office not reflected in One App for Move-in Requests created from App. | Closed | Mohammad Tabreze Karimee | Move in | 1 - Critical | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8851
8896 | Bug | Backoffice: Company Trade License upload field is missing in HHO Company Request Creation form | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8896
8897 | Bug | Backoffice: People of Determination field not reflecting correctly in Back-office for Owner requests created from One App. | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8897
8841 | Bug | Backoffice: Move-in: Occupant Move-in section incorrectly visible in HHO Unit & HHO Company request creation form | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8841
8842 | Bug | Backoffice: Breached SLA filter incorrectly includes request with status RFI Pending. | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8842
8843 | Bug | Backoffice: Move-in: Approval confirmation pop-up does not close after clicking Yes or No | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8843
8844 | Bug | BackOffice: Move-In: While creating move-in request from OneApp for HHO Unit Owner, Correct move-in type is not displayed on dashboard. | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8844
8845 | Bug | Backoffice: Highlighted text under People of Determination section in Tenant Move-in Request form does not match Figma | Closed | Mohammad Tabreze Karimee | Move in | 4 - Low | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8845
8846 | Bug | Backoffice: Toggle button design under Occupant Move-in section in Move-in Request creation form does not match Figma | Closed | Mohammad Tabreze Karimee | Move in | 4 - Low | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8846
8759 | Bug | When creating request from Backoffice portal, under "People of Determination" section, error message appears upon submission, even when details are entered. The issue occurs because text entered is not retained. | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8759
8760 | Bug | When creating a Tenant Move-In Request from Backoffice Portal and One App, after filling in all required details (Move-In Details, Occupants, etc.) and clicking Done, the entered data disappears, and no request is submitted. | Closed | Krishnan Kannan | Move in | 1 - Critical | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8760
8761 | Bug | Backoffice: Move-In: The filters on the Move-In Request list screen (e.g., Breached SLA, New, RFI Pending, Total Requests) are not functioning correctly. | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8761
8762 | Bug | Backoffice: Move-IN: While creating a Move-In for Tenant, when a valid email ID is entered, the field is unresponsive | Closed | Krishnan Kannan | Move in | 1 - Critical | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8762
8763 | Bug | Backoffice: Move-In: On the Move-In Request Dashboard, property-related fields (Master Community, Community, Tower/Street) are displayed as blank for each request. | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8763
8764 | Bug | Backoffice: Breadcrumbs name should be Proper. Make HHO and U in Unit in capital letter | Closed | Mohammad Tabreze Karimee | Move in | 5 - Suggestion | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8764
8765 | Bug | Backoffice: In HHO and HHC while creating Move In request, User is not able to select any of the community and hence unable to create a request | Closed | Krishnan Kannan | Move in | 2 - High | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8765
8766 | Bug | Backoffice: Move-In: When editing an existing Move-In Request, the updated details are not saved. | Closed | Mohammad Tabreze Karimee | Move in | 2 - High | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8766
8767 | Bug | Backoffice: Move-In: While creating a Move-In Request, clicking on the Create Request button does not directly open the form. | Closed | Mohammad Tabreze Karimee | Move in | 4 - Low | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8767
8768 | Bug | Backoffice: Move-In: When accessing a Move-In Request (either through View Request or while editing request), the uploaded documents cannot be viewed. | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8768
8769 | Bug | Backoffice: Move-IN: On the Create Move-In Request form, under the Occupants Move-In section, additional/unnecessary information is being displayed. | Closed | Krishnan Kannan | Move in | 1 - Critical | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8769
8770 | Bug | Backoffice: Move-In: When creating Move-In Request from Backoffice, properties with inactive Welcome Pack are still displayed in property selection drop-down. | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8770
8771 | Bug | One App: Move-IN: When creating a Move-In Request from the App, properties that have an inactive Welcome Pack are still available in property selection list. | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8771
8612 | Bug | The "History" button is currently unresponsive. When clicked, it does not perform any action or open the expected history details, preventing users from viewing the related records. | Closed | Mohammad Tabreze Karimee | Master Data Setup | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8612
8613 | Bug | When attempting to edit a Welcome Pack and change the Master Community, the system returns an error message: "Unknown error occurred". | Closed | Mohammad Tabreze Karimee | Master Data Setup | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8613
8614 | Bug | On the Upload Welcome Page screen, the Welcome Pack file label and the file upload label are not aligned properly. The "Upload Welcome Pack" label appears twice — one as the field label and again above the input box, creating inconsistency in the UI. | Closed | Mohammad Tabreze Karimee | Master Data Setup | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8614
8615 | Bug | When attempting to upload an HTML file on the Upload Welcome Page screen, the system keeps showing a continuous loading state and does not complete the upload process. | Closed | Mohammad Tabreze Karimee | Master Data Setup | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8615
8616 | Bug | Clicking on the MIP/MOP Template link results in a 404 error, preventing users from accessing the template. | Closed | Mohammad Tabreze Karimee | Master Data Setup | 1 - Critical | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8616
8617 | Bug | Clicking on the Move Out, Account Renewal, and Active Residents options does not trigger any action. The system remains unresponsive, and no related pages or data are loaded. | Closed | Mohammad Tabreze Karimee | Occupancy Request | 1 - Critical | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8617
8618 | Bug | Clicking on the Email Recipients option does not trigger any action. The system remains unresponsive, and no related data is displayed. | Closed | Mohammad Tabreze Karimee | Master Data Setup | 1 - Critical | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8618
8619 | Bug | In the Edit section of the New Move-In Request, the user is unable to save the changes made to the "Occupants Move-In" details. The system does not display any confirmation or error message, and the updated information is not saved. | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8619
8620 | Bug | In the Edit section of the Move-In Request in "New status", the Yes/No toggle button in Occupants Move-In Details is not working properly. | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8620
8621 | Bug | When clicking on Create Request under the Move-In section, the system displays an error message at the top: "ProfileUpdateId must be a number", and the request creation process fails. | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8621
8622 | Bug | The Created Date and Move-In Date displayed in the Move-In Request section are not following the date format specified in the BRD. As per the requirement, the format should be DD/MM/YYYY, but the system is currently displaying it as YYYY-MM-DD. | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8622
8757 | Bug | In the Move-In section, clicking on View button simply refreshes the page instead of displaying the request details. This issue occurs only after the user make changes to a Move-In request and then navigates back to the Move-In main page. | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8757
8785 | Bug | Backoffice: Welcome Pack: Editing the Welcome Pack returns error message | Closed | Rahees Khan | Master Data Setup | 2 - High | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8785
8786 | Bug | Backoffice: Default value in Status field not set to "Active" while creating new Email Recipient configuration | Closed | Mohammad Tabreze Karimee | Master Data Setup | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8786
8793 | Bug | Backoffice: Invalid date format error shown when creating a new Move-in Request for HHO Company. | Closed | Krishnan Kannan | Move in | 1 - Critical | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8793
8794 | Bug | OneApp: HHO: User is not able to create a Move In request from One App | Closed | Mohammad Tabreze Karimee | Move in | 1 - Critical | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8794
8795 | Bug | Backoffice : Move-In: User Details Not auto- Populating or Editable in HHO Company Move-in Request creation form. | Closed | Mohammad Tabreze Karimee | Move in | 1 - Critical | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8795
8796 | Bug | Backoffice: Filter: Once user set the filter and view any details, going back to previous page remove the filter condition. | Closed | Mohammad Tabreze Karimee | Move in | 4 - Low | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8796
8797 | Bug | Backoffice: Move-in: Representative Name Field Exceeds Character Limit Without Validation In HHC request creation form. | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8797
8798 | Bug | Backoffice: Move-In Date Fields Allow Selection of Past Dates in Move-in Request Form for Tenant and HHO Company. | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8798
8799 | Bug | Backoffice: Move-In Date Field Allow Selection of Present Date in Move-in Request Form for Owner and HHO Unit | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8799
8801 | Bug | Backoffice: Refresh and Search Functionality Not Working on Move-in Dashboard. | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8801
8802 | Bug | Backoffice: Unit Not Visible for Certain Property Combinations While Creating Move-in Request for any user. | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8802
8803 | Bug | Backoffice: Move-In: Approval of Move-in Request Fails Due to Overlapping Request Error | Closed | Krishnan Kannan | Move in | 1 - Critical | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8803
8804 | Bug | Backoffice: Move-In: Unable to Submit HHC Move-in Request for User from Backoffice | Closed | Mohammad Tabreze Karimee | Move in | 1 - Critical | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8804
8805 | Bug | Backoffice: Move In: Month arrow in Date Picker is not behaving properly. Clicking on up and down arrow should not close the date picker until user select any date | Closed | Mohammad Tabreze Karimee |  | 4 - Low | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8805
8806 | Bug | Backoffice: Move-In: Extra Asterisk Shown in Master Community Field in Move-in Request Form for any User | Closed | Krishnan Kannan | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8806
8807 | Bug | Backoffice: Mismatch Between Move-in Request List View and Exported Excel Data | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8807
8808 | Bug | Backoffice: Move-In: Incorrect Button Label on Cancel Move-in Request Confirmation Pop-up | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8808
8809 | Bug | Backoffice: Move-IN: Edited Move-in Request Cannot Be Submitted Due to Validation Error. | Closed | Mohammad Tabreze Karimee | Move in | 1 - Critical | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8809
8810 | Bug | Backoffice: Move-In: Occupant number incorrectly shows as 0 while editing move-in request for HHO unit and HHO company. | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8810
8811 | Bug | Backoffice: Move-IN: Occupant Details showing as "NA" for HHO Company move-in requests. | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8811
8812 | Bug | Backoffice: Move In: Clicking on NEXT Button without entering comment on View New MoveIn Request-> Cancel, returns multiple validation error message. | Closed | Mohammad Tabreze Karimee |  | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8812
8813 | Bug | BackOffice: “In the Move-In dashboard, when selecting the Export option as CSV, the system downloads the file in Excel (.xlsx) format instead of the expected CSV (.csv) format." | Closed | Mohammad Tabreze Karimee |  | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8813
8814 | Bug | BackOffice: MoveIn: User unable to select Status in Search Functionality | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8814
8773 | Bug | Back office: Move-In: Cursor focus auto pops out as soon as user enter any character | Closed | Krishnan Kannan | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8773
8774 | Bug | Backoffice: Move-In: The search functionality on the Move-In Dashboard is not working. | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8774
8775 | Bug | Backoffice: Move-In: While creating a request, the field-level validations for date fields are inconsistent between Figma design and live website. | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8775
8776 | Bug | Backoffice: Move-In: The Emirates ID number validation is inconsistent between Figma design and live website. | Closed | Mohammad Tabreze Karimee | Move in | 4 - Low | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8776
8777 | Bug | Backoffice & OneApp : Move-In: In the Tenant/Owner/HHO Unit Move-In Request creation form, the Move-In Type field is missing. | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8777
8778 | Bug | Backoffice: Move In: In the Owner Move-In Request creation form, the Move-In Date field validation is incorrect. | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8778
8779 | Bug | Backoffice: Move-In: In the Request creation form (for all user types), the mandatory fields are not marked with an asterisk (*). | Closed | Krishnan Kannan | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8779
8780 | Bug | Backoffice: Move-In: In the Move-In Request creation form (Owner), the Owner Details section is being prefilled with Super Admin account details | Closed | Mohammad Tabreze Karimee | Move in | 1 - Critical | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8780
8781 | Bug | Backoffice: Move-IN: In the Move-In Request creation form (for any user type), under the Occupants Move-In section, the counters for Adults, Children, and Pets allow adding unlimited numbers. | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8781
8782 | Bug | Back office: Move In: Clicking on Edit button Move In Tenant returns Application error message | Closed | Mohammad Tabreze Karimee | Move in | 1 - Critical | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8782
8783 | Bug | Back office: MoveIn: User unable to view the Cancelled Request done for Tenant | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8783
8816 | Bug | Backoffice: Move-in: Unwanted text appearing in Move-in Request Creation form of HHO company under Move-in Details section | Closed | Mohammad Tabreze Karimee | Move in | 4 - Low | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8816
8817 | Bug | Backoffice: Move-In: Email ID field in HHC form is not editable due to cursor auto pop-out issue | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8817
8818 | Bug | Backoffice: Move-in: Date fields are not editable in HHC Move-in Request creation form | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8818
8819 | Bug | Backoffice: MoveIn- Occupants Move in section have logic error while entering number of Pets | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8819
8820 | Bug | Backoffice: Move-In: Uploaded image preview displays file information overlay on middle of the image | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8820
8821 | Bug | BackOffice: Move-In: Owner details are not being auto-populated when entering the unit details during the Move-In process | Closed | Mohammad Tabreze Karimee |  | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8821
8822 | Bug | Backoffice: Move-in: Nationality field missing in Move-in Request Creation form but displayed as NA in request details | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8822
8823 | Bug | Backoffice: Move In: Move in Screen displays "Apply" button in black color which gets gray while hover. | Closed | Mohammad Tabreze Karimee |  | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8823
8825 | Bug | Backoffice: Move-in: Move-In Details and Unit Permit Details sections missing in View mode for HHO Company requests | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8825
8826 | Bug | Backoffice: Movein: Toggle button is gray when enabled | Closed | Mohammad Tabreze Karimee | Move in | 4 - Low | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8826
8827 | Bug | Back Office: Move In: Occupants Move in Section labels should be in gray color"(Above 12 Years) *" | Closed | Mohammad Tabreze Karimee | Move in | 4 - Low | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8827
8828 | Bug | Backoffice: Move-In: Tenancy Contract Number & Unit Permit Number fields allow special characters in Tenant and HHO Owner forms | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8828
8829 | Bug | BackOffice: Move-In: While editing the Move-In request for Tenant, It is asking to re -upload the document. | Closed | Mohammad Tabreze Karimee | Move in | 2 - High | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8829
8830 | Bug | Backoffice: Move in: If overlapping move-in requests exist, a popup with their count must be shown to the Community Admin. | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8830
8831 | Bug | Backoffice: Move-in: Tenancy Contract Number not displayed in View mode for Tenant move-in requests | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8831
8832 | Bug | Backoffice: Move in : Submitting Move in request returns validation error for few Units number | Closed | Krishnan Kannan | Move in | 2 - High | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8832
8833 | Bug | Backoffice: Filters alignment issue on Move-in Dashboard | Closed | Mohammad Tabreze Karimee | Move in | 4 - Low | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8833
8834 | Bug | Backoffice: Count mismatch in “New” filter on Move-in Dashboard | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8834
8835 | Bug | Backoffice: Move in: In Move in Request submission, confirmation popups must display the Move-in Request Number | Closed | Mohammad Tabreze Karimee | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8835
8836 | Bug | Backoffice: Move in: User Owner has to click twice on Cancel button to go back to the screen | Closed | Mohammad Tabreze Karimee |  | 4 - Low | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8836
8837 | Bug | Backoffice: Move-in request can be created without active MIP template and Welcome Pack for Master Community. | Closed | Mohammad Tabreze Karimee | Move in | 1 - Critical | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8837
8838 | Bug | Backoffice: Misaligned “Move in X Steps” text in Owner card on Move-in landing page | Closed | Mohammad Tabreze Karimee | Move in | 4 - Low | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8838
8839 | Bug | Backoffice: Move in: Clicking on Reset Button, application does not reset the "People of determination" toggle button | Closed | Mohammad Tabreze Karimee | Move in | 4 - Low | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8839
8840 | Bug | BackOffice: Move-In: Form Fields available in HHC Company is not following the Form Field validation. | Active | Krishnan Kannan | Move in | 3 - Medium | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8840
8824 | Bug | Backoffice: Move-in: Duplicate Move-in Type field displayed while editing Tenant move-in request. | Active | Krishnan Kannan | Move in | 4 - Low | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8824
8784 | Bug | Backoffice: MoveIn: Clicking on Submit button multiple times without entering comment returns multiple warning message. This message should be displaying only one time | Active | Krishnan Kannan | Move in | 5 - Suggestion | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8784
8815 | Bug | Backoffice: Move-in Date field is not properly aligned in the Move-in Request Creation form of Tenant and HHO company | Active | Krishnan Kannan | Move in | 4 - Low | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8815
8772 | Bug | Backoffice - Move In: Clicking Export All downloads file as data.xlsx instead of MoveIn.xlsx, and it includes irrelevant columns. | Active | Krishnan Kannan | Move in | 5 - Suggestion | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8772
8930 | Bug | Backoffice: Movein: Breadcrumb "Dashboard should be replaced by "Occupancy Request" which should be non clickable | Active | Krishnan Kannan | Move in | 4 - Low | https://dev.azure.com/SobhaRealty/OneApp/_workitems/edit/8930